## Sheet1
| Sr.No | Task Description | Start Date | Finish Date | Duration
| 1 | Installing Updated Softwares & updated windows | 2020-06-02 | 2020-06-03 | 1
| 2 | 1st meeting with supervisor | 2020-06-03 | 2020-06-04 | 1
| 3 | Completing Terms Of Reference & Ethich form | 2020-06-04 | 2020-06-09 | 5
| 4 | 2nd meeting with supervisor | 2020-06-09 | 2020-06-10 | 1
| 5 | 1st meeting with the client | 2020-06-09 | 2020-06-10 | 1
| 6 | Gathering requirements from client for the project | 2020-06-10 | 2020-06-11 | 1
| 7 | Writing the introduction part | 2020-06-11 | 2020-06-13 | 2
| 8 | Acquiring References | 2020-06-13 | 2020-06-14 | 1
| 9 | 3rd meeting with supervisor | 2020-06-13 | 2020-06-14 | 1
| 10 | Writing background and Literature review of project | 2020-06-14 | 2020-06-16 | 2
| 11 | Writing on research methodologies | 2020-06-16 | 2020-06-18 | 2
| 12 | Creating templates of website | 2020-06-18 | 2020-06-20 | 2
| 13 | 2nd meeting with client | 2020-06-20 | 2020-06-21 | 1
| 14 | Working on client feedback | 2020-06-21 | 2020-06-22 | 1
| 15 | Converting html template into MVC bootstrap | 2020-06-22 | 2020-06-30 | 8
| 16 | Testing of MVC converted templates | 2020-06-30 | 2020-07-02 | 2
| 17 | 4th meeting with supervisor | 2020-07-02 | 2020-07-03 | 1
| 18 | 3rd meeting with client | 2020-07-03 | 2020-07-04 | 1
| 19 | Gathering contents for static web pages from client | 2020-07-04 | 2020-07-06 | 2
| 20 | Adding contents to the static web pages | 2020-07-06 | 2020-07-09 | 3
| 21 | Desigining of static web pages | 2020-07-09 | 2020-07-14 | 5
| 22 | Testing of web pages | 2020-07-14 | 2020-07-16 | 2
| 23 | 5th meeting with supervisor | 2020-07-16 | 2020-07-17 | 1
| 24 | 4th meeting with client | 2020-07-17 | 2020-07-18 | 1
| 25 | Working on client feedback | 2020-07-18 | 2020-07-19 | 1
| 26 | Planning and desigining of dynamic web pages | 2020-07-19 | 2020-07-21 | 2
| 27 | Developing a data warehouse on MS SQL | 2020-07-21 | 2020-07-25 | 4
| 28 | C# Programming for dynamic web pages | 2020-07-25 | 2020-07-31 | 6
| 29 | Data repository method calls to perform DML transactions | 2020-07-31 | 2020-08-05 | 5
| 30 | 6th meeting with supervisor | 2020-08-05 | 2020-08-06 | 1
| 31 | 5th meeting with client | 2020-08-06 | 2020-08-07 | 1
| 32 | Working on client feedback | 2020-08-07 | 2020-08-09 | 2
| 33 | Testing all the web pages | 2020-08-09 | 2020-08-14 | 5
| 34 | Writing on project implementation | 2020-08-14 | 2020-08-19 | 5
| 35 | Describing testings and findings | 2020-08-19 | 2020-08-25 | 6
| 36 | Writing conclusion | 2020-08-25 | 2020-08-27 | 2
| 37 | 7th meeting with supervisor | 2020-08-27 | 2020-08-28 | 1
| 38 | 6th meeting with client | 2020-08-29 | 2020-08-30 | 1
| 39 | Reviewing the project | 2020-08-30 | 2020-09-02 | 3
| 40 | Submit the project | 2020-09-03 | 2020-09-04 | 1
Min | Max
43984 | 44078